## Sheet1
Aldi Suggestions
Date | Defect Number | Defect raised by | Sprint part of | Workbench | Screen | Defect Description | Type | Cityon Status | Cityon Feedback | Fix Date | ALDI Retest Feedback
2022-05-20 | D004 | CP2 Project Team | 6 | Admin Workbench | Automated Trigger builder | Lead Time should give a dropdown list of available fields to choose the lead time from | Functional | Open | Awaiting List of Lead Time dropdown values |  | Lead Time values should be based on ALL fields with a Date format.
2022-05-20 | D023 | CP2 Project Team | 6 | Admin Workbench | Free Text Maintenance List | 1. Free Text Maintenance List - progress shows 50% but there are 3 Screens. When we complete the first two screens, this shows 100% complete. 2. Screens 2 and 3 are not mandatory. 3. Could we have a tickbox for "N/A" in both screens. 4. You would have a choice: "N/A" or "Distribution List". If "Distrubution List" is ticked, then we need a stream / receiver group to be selected. The applies for categories as well. If "N/A" is selected, the screen is complete without a Distribution List / Category being assigned. | Functional | Open | Progress Bar has been updated.
2022-05-23 | D026 | CP2 Project Team | 6 | Admin Workbench | Automated Trigger Condition Functions | The functional side needs changing: a) when you delete the first line of a condition, the whole condition is deleted. b) when you press save, it only saves if you have confirmed each line. | Functional | Open | This requirement needs significant changes in existing functionality, this will be resolved in the upcoming sprint.
2022-05-23 | D030 | CP2 Project Team | 6 | Admin Workbench | Receiver Group Maintenance | Article Hierarchy should be a tick box of the available product hierarchies | Functional | Open | Awaiting List of Product Heirarchies |  | The list is "Core" "Special Buy" "Seasonal" "Country Specific". This has been provided already. T179 in SAP.
2022-06-21 | D039 | CP2 Project Team | 7 | Free Text Trigger Workbench | Free Text Trigger Workbench | We are not able to adjust the column widths, or the window sizes. This was agreed previously. | UI | Open
2022-06-21 | D041 | CP2 Project Team | 7 | Free Text Trigger Workbench | Free Text Trigger Workbench | When we gave our feedback, we wanted the message to appear within the screen - our screen size should not change. We also don't want the "message" to be the width of all the columns. The message should be fixed, regardless of if there is a left / right scrollbar. | UI | Open
2022-06-21 | D043 | CP2 Project Team | 7 | Free Text Trigger Workbench | Free Text Trigger Workbench | We require something to indicate that there are notes for this messages. | Functional | Open
2022-06-21 | D053 | CP2 Project Team | 7 | Free Text Trigger Workbench | Free Text Trigger Workbench | Notes do not appear when printing out | UI | Open
2022-06-21 | D057 | CP2 Project Team | 7 | Free Text Trigger Workbench | Free Text Trigger Workbench | Message Rejected (No "Reject Comment" requested, and the "Record Updated Successfully" but the status is still "Awaiting Approval" | Functional | Open
2022-06-21 | D058 | CP2 Project Team | 7 | Free Text Trigger Workbench | Free Text Trigger Workbench | Notes do not update once a message has been "Rejected" | Functional | Open
2022-06-21 | D063 | CP2 Project Team | 7 | Free Text Trigger Workbench | Free Text Trigger Workbench | Any events with "0" should move to the bottom and be greyed out. Also what is the logic for the ordering of the FT Events? We believe that this should be FT001, FT002, FT003 etc | Functional | Open
2022-06-21 | D069 | CP2 Project Team | 7 | Free Text Trigger Workbench | Free Text Trigger Workbench | When we go to press Submit, it shows as "Please select Stream and Receiver Group" | UI | Open | The Selection was not done, that's why the submit was disabled
2022-06-21 | D071 | CP2 Project Team | 7 | Free Text Trigger Workbench | Free Text Trigger Workbench | Message Preview page - Please show receiver Groups | UI | Open
2022-06-21 | D073 | CP2 Project Team | 7 | Free Text Trigger Workbench | Free Text Trigger Workbench | Field should read "Status" not "Approval Status" and "Ready" is not a Status in the Free Text Workbench | UI | Open
2022-06-21 | D074 | CP2 Project Team | 7 | Free Text Trigger Workbench | Free Text Trigger Workbench | Logic needs to be clarified over "Posted Date" | UI | Open | ALDI Needs discussion
2022-06-22 | D079 | CP2 Project Team | 6 | Admin Workbench | Trigger Builder | We should be able to add a line to an exisiting function, in case we need to add more. | Functional | Open
2022-06-22 | D080 | CP2 Project Team | 6 | Admin Workbench | Trigger Builder | Entering a condition is Mandatory on the system. Some triggers may not need a condition. | Functional | Open
Open
[6 empty] | We should have an On / Off button to indicate if a condition is needed similar to the one for Lead Time available. If condition is Greyed out (Off), then the "Condition Functions tab should be green. If it is turned on, then the tab is yellow. |  | Open
Open
[6 empty] | By default , this should be "ON", which means someone either has to enter a condition or to turn the conditions OFF in order be "Complete / Green" |  | Open
2022-06-22 | D085 | CP2 Project Team | 6 | Admin Workbench | Admin Workbench | Default number of entries on a page - Can we have by default 50 entries per page for all Admin Workbench entries (Automated Trigger, Receiver Group, Free Text, Category). | UI | Open
2022-06-22 | D087 | CP2 Project Team | 6 | Admin Workbench | RG Maintenance - Add Trigger | Product Hierarchy to be updated with real data (as a tick box function) | Functional | Open